I-GUIDE TOOL FOR MANAGEMENT OF ETHICAL GEOSPATIAL AI AND DATA SCIENCE (I-GUIDE MEG-AID)

The I-GUIDE Tool for Management of Ethical Geospatial AI and Data Science (I-GUIDE MEG-AID) is a practical project management tool designed to help research teams navigate ethical, legal, and reproducibility-related decisions across the full span of a geospatial project. It aligns with the I-GUIDE lifecycle stages, from defining the research problem through to sharing results.

MEG-AID does not list every activity undertaken in a project. Rather, it focuses on actions that raise ethical, legal, or reproducibility concerns. MEG-AID is most useful when integrated into project planning from the beginning. Many actions are difficult to reverse once work is underway. Revisit MEG-AID regularly. The tool is designed to be updated throughout the project.

### Understanding the Columns

- Action: A concrete step you should take that has potential ethical, legal, or reproducibility consequences;

- Person Responsible: Who on the team is accountable for carrying out or overseeing this action;

- Status: Tracking progress on taking the action – input “Pending”, “In Progress” or “Completed” as appropriate.

### MEG-AID Attribution and License

The MEG-AID (Managing Ethics and Governance Across the I-GUIDE Lifecycle) tool was developed specifically for the I-GUIDE platform to support responsible, reproducible, and ethical research throughout the data and model lifecycle.

This work is licensed under a Creative Commons Attribution-ShareAlike 4.0 International License (CC BY-SA 4.0).
License details: https://creativecommons.org/licenses/by-sa/4.0/

- DEFINING THE RESEARCH PROBLEM

| Action | Person Responsible | Status |
| --- | --- | --- |
| Optional: Engage with stakeholders to refine or co-produce research goals (e.g., via focus groups, workshops, surveys, participatory mapping) |  |  |
| Create I-GUIDE Research Product Management Plan Only complete fields for which you have information |  |  |

- DATASET ACQUISITION AND CREATION

2a. Acquiring Secondary Datasets

| Action | Person Responsible | Status |
| --- | --- | --- |
| Create Data Card for each secondary dataset Only complete fields for which you have information |  |  |

2b. Collecting or Generating Primary Datasets About Non-Human Subjects

| Action | Person Responsible | Status |
| --- | --- | --- |
| Create Data Card for each primary dataset about physical phenomena Only complete fields for which you have information |  |  |

2c. Collecting or Generating Primary Datasets About Human Subjects

| Action | Person Responsible | Status |
| --- | --- | --- |
| Design a clear, straightforward informed consent process Consent materials: Recruitment message for participants; Method of giving information about your study to prospective participants; Method of recording informed consent |  |  |
| Address demographic and geographic fairness Recruitment strategy for hard-to-reach populations; Consent materials tailored to hard-to-reach populations |  |  |
| Develop strategies to ensure populations, such as children or non-native speakers, can understand consent materials Simplified or translated materials and research instruments (e.g., interview questions, surveys) |  |  |
| Secure Institutional Review Board (IRB) approval |  |  |
| Obtain and store informed consent from participants Store hard copies in a locked filing cabinet. Store digital copies in a folder on IRB-compliant server |  |  |
| Create Data Card for each primary dataset Only complete fields for which you have information |  |  |

2d. Collecting Primary Datasets from Web Scraping or other Digital Activities

| Action | Person Responsible | Status |
| --- | --- | --- |
| Verify that scraping complies with platform policies |  |  |
| Secure Institutional Review Board (IRB) approval if necessary Check if you need IRB approval here: https://www.hhs.gov/ohrp/regulations-and-policy/decision-charts-2018/ |  |  |
| Identify limitations in the geographic and/or demographic representativeness of your dataset |  |  |
| Create Data Card for each primary dataset Only complete fields for which you have information |  |  |

- PROCESSING AND CLEANING DATA

| Action | Person Responsible | Status |
| --- | --- | --- |
| Record data processing steps Keep a running log or simple spreadsheet |  |  |
| Test variables to see if any correlate with demographic groups Use simple statistical tests and visualizations (e.g., scatterplots) |  |  |
| Take debiasing actions to mitigate geographic or demographic bias detected, where possible |  |  |
| Anonymize or de-identify personally identifiable data |  |  |

- STORING DATA

| Action | Person Responsible | Status |
| --- | --- | --- |
| Select a storage system compliant with funding agency and institutional policies Non-sensitive data -> own computer or laboratory server; Sensitive data -> secure institutional cloud storage with controlled access |  |  |

- MODEL ACQUISITION AND CREATION

5a. Acquiring Existing Model

| Action | Person Responsible | Status |
| --- | --- | --- |
| Create Model Card for each acquired model Only complete fields for which you have information |  |  |

5b. Building and Training a Custom Model

| Action | Person Responsible | Status |
| --- | --- | --- |
| Assess the demographic and geographic representativeness of datasets used to train the model |  |  |
| Assess the model’s transparency, explainability, and interpretability |  |  |
| Consider what other ethical issues might arise from use of the model E.g., surveillance, privacy threats, consent of those affected by model-supported decision-making, potential inappropriate uses of the model |  |  |
| Create Model Card for each model you or your team build Only complete fields for which you have information |  |  |

- INTEGRATING MULTIPLE MODELS INTO A SINGLE MODEL

| Action | Person Responsible | Status |
| --- | --- | --- |
| Assess the demographic and geographic representativeness of datasets used to train the model |  |  |
| Assess the model’s transparency, explainability, and interpretability |  |  |
| Validate the model |  |  |
| Consider what other ethical issues might arise from use of the model E.g., surveillance, privacy threats, consent of those affected by model-supported decision-making, potential inappropriate uses of the model |  |  |
| Create Model Card for each model you or your team create by integrating two or more other models Only complete fields for which you have information |  |  |

- GENERATING AND INTERPRETING MODEL OUTPUTS

| Action | Person Responsible | Status |
| --- | --- | --- |
| Update Research Product Management Plan, Data Cards, and Model Cards |  |  |

- DISSEMINATING, ARCHIVING, OR DESTROYING, RESEARCH OUTPUTS

| Action | Person Responsible | Status |
| --- | --- | --- |
| Clearly explain limitations and uncertainties of datasets and models in presentations, reports, and papers |  |  |
| Communicate with affected stakeholders in a way that helps their understanding E.g., plain language summaries for non-experts; translations for non-native speakers; clear visualizations; meetings with stakeholder groups |  |  |
| Assess which data, models, and research outputs should be shared, archived - Relevance: Still useful? - Sensitivity: Private, proprietary, or regulated data? - Compliance: Are there policies governing retention or deletion? |  |  |
| Securely destroy data and models when necessary |  |  |
| Archive data and models in trusted open-access repositories, with their respective Data and Model Cards |  |  |
| Ensure persistent identifiers are assigned (DOI) to datasets and models |  |  |
| Evaluate datasets’ compliance with the FAIR (Findable, Accessible, Interoperable, Reproducible) Principles F-UJI tool for automated evaluation of dataset compliance: https://www.f-uji.net/ |  |  |
| Complete, revise, and finalize Research Project Management Plan, Data Cards, and Model Cards |  |  |